## Introduction
Stakeholder and Relationship Maps
The information in this tool will help you identify your stakeholders and approach to involving them in your change.
You may decide not to use each tab, do what best suits your needs and change programme.
Tab 2: Your stakeholders. Use this to list/summarise those affected by your change
Tab 3: Stakeholder engagement. Classify your stakeholders by considering their power and interest
Tab 4: Template - Plan Activities. Set out how you plan to involve/manage your stakeholders
Tab 5: Managing Relationships. Set out any key relationships between your stakeholders
Tab 6: Relationship Map. This can be used to capture the groups that are affected. This can work well in a workshop or as prompt to make you think of who may be affected
Tab 7: Relationship Interactions. Can be used to capture the nature of the relationship (direct or indirect) between stakeholders
Tab 7: Stakeholder workshop. You may use this tab in a workshop or present the information in a creative way

## 2) Your stakeholders
Stakeholder No | Stakeholder Name/Group | Known Information/Position | Unknown/Info to Validate
|  | (Where the stakeholder is currently positioned) | (Other information to find out)
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16 |  |  | Extend table as appropriate ...

## 3) Stakeholder Engagement
Quadrant 3 - Keep Satisfied
Quadrant 1 - Monitor
Quadrant 4 - Manage Closely
Quadrant 2 - Keep Informed
To add information right click on each box and choose 'Edit Text'
Note that these pages are set-up as landscape (A3) Only the quadrant will print (view the page layout tab to change this if required)
Scroll down for brief guidance on each Quadrant
Commitment
Ownership, action, influencing others
Problem solving teams, business objectives review, workshops, feedback and review sessions
Involvement
Ideas, participation, two-way feedback
Managers briefings, employee forums, competitions, workshops, recognition, transition planning
Support
Business change is something that can be supported through attitude and behaviour
Leadership team briefings, conferences, open forum, site visits, readiness surveys, evaluation surveys
Understanding
Why? The reason for business change
Face-to-face briefings, ‘day in life’ scenarios, notice board, local newsletter, benefits poster
Awareness
The need to know something has changed
Newsletters, FAQs, countdown posters, intranet promotion
DEGREE OF INVOLVEMENT
IMPACT OF CHANGE
Guidance: For further information see the presentation in the BCF
Quadrant 1 – ‘Monitor’
Stakeholders in this quadrant do not have direct involvement or interest in the change project.
Build a general awareness of the change. Monitor these stakeholders, but do not send them excessive communications.
Quadrant 2 – ‘Keep Informed’
Stakeholders in this quadrant are likely to be major users of the change project outputs and need both awareness and understanding of the change.
Engage them enough to secure their satisfaction, where reasonable. This type of stakeholder can often be very helpful with the detail of the change.
Quadrant 3 – ‘Keep Satisfied’
Stakeholders in this quadrant are unlikely to have direct contact with the change outputs, but they have high influence due to their position in the organisation.
Keep them adequately informed and ensure there is effective dialogue to avoid major issues arising, but do not give them more information than they want to receive.
Quadrant 4 – ‘Manage Closely’
Stakeholders in this quadrant are key players in the change. Fully engage with them and make the greatest efforts to satisfy them.
Ensure a developed understanding of the change and full involvement/commitment to it.
Commitment Escalator
See below for ideas on involvement and increasing understanding. Consider what is appropriate and realistic for the phase of your change. For example, early on you may need people to be aware of the changes but by the Deliver Phase you may need stakeholders to be fully involved or commited

## 4) Template - Plan activities
Stakeholder Name/Group | Their Key Interests | Objectives | Communications Requirements | Key Channels | Owner and Feedback Mechanism | Issues/Status
|  | What do we want them to... | Opportunities and Risks/Barriers
Q4 Manage Closely
eg |  | Feel... | To do this they need... | eg
Programme Top Teams |  | - eg Confident in project delivering the right change for their area | eg | - Monthly briefings 1:1
Lead Sponsors |  | Know... | - Clarity on their role | - Project communications pack
Programme Managers |  | - eg What the project is delivering and how it will make a difference (including imperative for change) | - Regular focused updates/briefings | - Staff briefings
|  | Do... | - Involvement in process - opportunity to ‘co-create’ solution
|  | - eg Be Fully involved and influential in making the change happen | - Confidence in supporting evidence and data
What might prevent them...?
eg
- Competing priorities in own business area
- Ineffective change leadership
Q3 Keep Satisfied
eg |  | Feel... | To do this they need... | eg
Project Managers |  | - eg They are consulted with at right times | eg | - Monthly briefings
Project Engineers |  | Know... | - Regular programme updates | - Staff briefings
|  | - eg Have a clear view of what changes are being proposed and the staff who are involved in the process | What might prevent them ...?
|  | Do... | eg
|  | - eg Provide feedback – both positive and negatives to enable change to be managed better | - Lack of understanding of what is expected of them
- Lack of resources available
Q2 Keep Informed
eg |  | Feel... | To do this they need... | eg
Other functional Heads |  | - eg Confident that project is delivering right change for the business | eg | - Monthly briefings
|  | Know... | - Accurate, well presented updates on the programme | - Staff briefings
|  | - eg How the project is progressing, including any change to realising the benefits | - To be engaged with at right level
|  | Do... | What might prevent them...?
|  | - eg Make informed decisions that help to progress the programme | eg
- Competing priorities
- Conflicts of interest
Q1 Monitor
eg |  | Feel... | To do this they need... | eg
Other functions – eg Legal, Comms |  | - eg Informed and ‘in the know’ about the changes | eg | - Emails
|  | Know... | - The right level of information at the right time | - Team/General briefings
|  | - eg What they need to do to support the project | What might prevent them...? | - Intranet articles
|  | Do... | eg
|  | - eg Take the necessary actions to support the project | - Lack of buy-in or interest in the project
- Project not a priority

## 5) Managing Relationships
Key relationship between (a) | and (b) | Nature of Relationship | Further details if required | Why is this an important relationship/How will it impact upon your change? | How can you manage this relationship?
Director of Dept X | Head of Dept Y | Indirect | Used to work together | Head of Dept Y is still seen as an expert on the topic and the Director will seek their opinion | Keep the Head of Dept Y updated in the options/change. Ensure they are in Quadrant 4 - Manage Closely
Head of ER | Union rep(s) | Direct | Manage the day-to-day relationship | Need to ensure we follow the correct approach to consultation | Ensure the Head of ER is in Quadrant 2 - Kept Informed
Head of Department X | External Supplier | Indirect |  | External Supplier can help us increase publicity | Request the Head of Dept X to set up an introduction
Sponsor | Head of Dept Y | Indirect | Working on a different project together but share information | Head of Dept Y influences the Sponsor on this project | Keep the Head of Dept Y updated in the options/change. Ensure they are in Quadrant 4 - Manage Closely
The work that you undertake on Relationship Mapping will really help add value to the outputs from your Stakeholder Plan. Whilst your Stakeholder Plan will help you identify current and desired outcomes from people, this activity will add further value by helping you:
Understand who influences who and why
Give you a true picture of why the change may be of interest to people
Construct a plan on how to manage these relationships
Ensure your approach to engaging with stakeholders is robust
Ensure that your proposed timings and content of updates are co-ordinated effectively
Does this change the quadrant
Rather than just looking at the stakeholders from a project point of view this allows you to consider how key stakeholders may interact between one another.
At first thought you may have believed that Head of Dept Y was not relevant to your change programme as they are not directly affected. However, upon closer review they may have a relationship or impact on several people.
Note that these pages are set-up as landscape (A3)
The text entered is an example only. Please amend as approporiate

## 6) Rel. Maps
Project Deliverable(s)
Name of Sponsor
Before you, embark on your change project you’ll need to review the project and compile a list of any groups that may be affected. The Group Review diagram will help you.
TIP: Many People find this easy to use if they print out this sheet and use it as a scribble pad to generate thoughts and ideas.
First of all, write down the aim of the project, and your sponsor, at the top of the page.
Then add the groups who’ll be affected by the changes e.g. first line managers, employees doing job A and B, Department X that provides a service to us (Employee Groups)
Next, make a note of the people who’ll need to support the delivery of the messages e.g. Change Champions (Change Roles)
And those who will need to help build the solution e.g. IM, HR, Commercial, IM (Solution Builders)
Finally, add any other significant interested parties e.g. trades unions. (Other)
See the People Change Roles and Responsibilities guidance in the Discover Phase for more detail.
Employee Group
Who is affected?
Change Roles
Who is helping delivery e.g Managers, Directors,?
Interested parties
Who else is affected?
Solution Builders
Who can help and/or should be involved?
Other thoughts/comments

## 7) Rel. Interactions
To develop the Managing Relationships (tab 5) and Relationship Map (tab 6) information further you may decided to use this approach to capture the relationships between the various groups and/or individuals. You should draw solid lines to indicate a direct relationship and a dotted line to indicate an indirect relationship. Some people may find this visual way of showing the individuals and relationships as useful. Perhaps more importantly it will help you capture and understand anyone that influences key stakeholders.
Tip: Keep this high level as too much detail could confuse matters. You can build on it at a later date or construct separate ones for different parts of your change. Think about the importance of your Sponsor and who they can influence and who influences them, but try not to think about organisation hierarchy. Make sure your end result is not a structure chart.
Employee Group ........
In each of the below boxes at the name of the individual or stakeholder group. Of course you may just choose to draw this free-hand.
Change Role:
Solution Builder:
Interested parties
Employee Group ........
Employee Group ........
Employee Group ........
Employee Group ........
Employee Group ........
Solution Builder:
Solution Builder:
Solution Builder:
Solution Builder:
Solution Builder:
Interested parties
Interested parties
Interested parties
Interested parties
Interested parties
Change Role:
Change Role:
Change Role:
Change Role:
Change Role:
Director of Dept A.
Head of Dept Y.
Head of ER
Head of Dept X
External Supplier
Based on tab 5 an example is set out below to show the interactions between the stakeholders. At first thought you may have believed that Head of Dept Y was not relevant to your change programme as they are not directly affected. However, upon closer review they may have a relationship or impact on several people. Therefore, think of how they may need to be involved/informed
Union Reps
Sponsor

## 8) Stakeholder -workshop
Quadrant 3 - Keep Satisfied
Quadrant 1 - Monitor
Quadrant 4 - Manage Closely
Quadrant 2 - Keep Informed
NAME HERE
NAME HERE
NAME HERE
NAME HERE
NAME HERE
NAME HERE
NAME HERE
NAME HERE
You may use this information in a workshop or present the information in a creative way.
Use the stars and place them in the appropriate quadrant.
Perhaps ask attendees at the workshop to place them seperatly - do you all agree on how they should be involved or managed? Ask who will manage the stakholder and how.